## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As a student I want to upload files (PDF, DOCX, plain text). | 1 |  |  | Planned
2 | As a student I want the text from uploaded files to be preprocessed (cleaning, segmentation). | 1 |  |  | Planned
3 | As a student I want uploaded files to be summarized using pre-trained open-source models (e.g. BART, T5). | 1 |  |  | Planned
4 | As a student I want questions to be generated for flashcards and quizzes. | 1 |  |  | Planned
5 | As a student I want to be able to use interactive quizes/flashcards. | 1 |  |  | Planned
6 | As a student I want my progress to be tracked (score history, completed sets) | 1 |  |  | Planned
7 | As a student I want an user account for saving study sessions. | 1 |  |  | Planned
8 | As a student I want to be able to publish and share flashcards and quizzes. | 2 |  |  | Planned
9 | As a university I want to create and manage an organization for students to be connected to. | 2 |  |  | Planned
10 | As a student I want to be able to work with multiple languages | 3 |  |  | Planned
11 | As a student I want to be able to use an exam mode. | 2 |  |  | Planned | Exam mode would simulate an exam and provide information about the amount of time spend on each part. Possibly includes a pause feature.

## Sprint 1
Sprint 1
Starts | 2018-11-08
Ends | 2018-11-28
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a registered user I want to set-up a personal profile page to present myself. | User can define and view profile page with profile picture and self description. |  |  |  | in process
done
to do
accepted
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Extend database with fields for profile info | 1 | 3 | 4.5 | done | Philipp Graf
2 | Develop form to fill in profile data in HTML | 1 | 6 |  | in process | Anja Müller
3 | Add form and logic for save / edit to application | 1 | 3 |  | to do

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required