## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As a student I want to upload lecture materials/notes to the website for studying. | 1 |  |  | Planned | Accept PDF, DOCX, and TXT files that are up to a certain size limit. (E.X. XXX KB)
2 | As a student I want my uploaded notes to be processed and summarized by NLP model. | 1 |  |  | Planned | This would involve text processesing such as text cleaning and segmentation. The NLP model should be open source.
3 | As a student I want flashcards and quizzes to be generated for my uploaded materials to use for studying. | 1 |  |  | Planned
4 | As a student I want interactive modes to allow me to effectively utilize the generated flashcards and quizzes. | 1 |  |  | Planned | An example of what these modes could look like is Quizlet.
5 | As a student I want to track my progress and performance to understand what I need to work on the most. | 2 |  |  | Planned
6 | As a student I want to have an account to save generated flashcards/quizzes. | 2 |  |  | Planned
7 | As a student I want to see statistics and other metrics about my activity and account. | 2 |  |  | Planned
8 | As a student I want to be able to publish and share my generated flashcards and quizzes. | 3 |  |  | Planned | This could involve sharing to an invidiual student, to the entire university, or to every user.
9 | As a university I want to create and manage an organization for students to be connected to. | 3 |  |  | Planned
10 | As an international student I want to be able to use the website in multiple languages to allow me to study in my native language. | 4 |  |  | Planned | We should at least add a framework so it would be easy to add more languages to the website.
11 | As a student I want to be able to use an exam mode to prepare for class exams. | 3 |  |  | Planned | Exam mode would simulate an exam and provide information about the amount of time spend on each part. Possibly includes a pause feature.
12 | As a student/university I want to be able to use/publish additional functionality from a plugin marketplace to improve my studying experience. | 4 |  |  | Planned | Examples of plugins could include additional AI models, such as ones trained for specific subjects or languages.
13 | As a student I want to be able to chat with an AI agent for explanations about topics I don't fully understand | 5 |  |  | Planned | Should be able to answer questions about topics from the provided/generated materials (Like the AI in textbook websites). Possibly allow it to see your statistics to give it context on the level of the person asking. This AI should have some level of memory to be able to at least answer follow up questions, there is a possibility to save chat instances so a student can return to a topic they asked about.
14 | As a student I want to be able to export the generated content for use outside of the website. | 4 |  |  | Planned | For use in making physical flashcards or doing a quiz on paper exporting to PDF would be the best option, if we want to allow importing of quizzes and flashcards we can create a JSON format for them.
15 | As a student i want to be guided around the app after onboarding to be introduced to the apps functionality | 4 |  |  | Planned | Onboarding tour explaining features to display apps capabilities
16 | As an organisation i want to connect to other organisations via federation to allow students and professors to benefit from materials and content published. | 6 |  |  | Not planned | In the sense of free and open education and research the marketplace and publishing content should not be limited by the organisations scope.
17 | As a Administrator i want to be able to connect to external authentication providers to have state of the art security by SSO. | 4 |  |  | Not planned | OIDC or OAuth or SAML2.0 should be available as authentication protocols to avoid overhead from user management.
18 | As a student i want the ability to chat with the AI model directly, this allows me to produce custom content, fine tune existing content or fill gaps in my knowledge. | 5 |  |  | Planned | direct chat mode
19 | As an Administrator i want to be able to easily install extensions via a unified plugin marketplace, since this allows me to extend/adjust functionality of the app as needed without extensive configuration. | 5 |  |  | Planned | unified layout for plugins with coherent configuration options

## Sprint 1
Sprint 1
Starts | 2018-11-08
Ends | 2018-11-28
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a registered user I want to set-up a personal profile page to present myself. | User can define and view profile page with profile picture and self description. |  |  |  | in process
done
to do
accepted
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Extend database with fields for profile info | 1 | 3 | 4.5 | done | Philipp Graf
2 | Develop form to fill in profile data in HTML | 1 | 6 |  | in process | Anja Müller
3 | Add form and logic for save / edit to application | 1 | 3 |  | to do

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required